**NATIONAL TIMETABLE FOR CURRICULUM 2024 – IMPLEMENTATION NOTE NO 8**

**Purpose of this Note**

This Implementation Note is intended to provide a timetable against which trainee ophthalmologists, Heads of School and TPDs can plan for the launch of Curriculum 2024. It has been drawn up in consultation with the Training Programme Directors and approved for circulation by the OST Project Board (OPB).

|  |  |
| --- | --- |
| **Date**  | **Activity**  |
| 31 August 2023  | * All trainees must inform HoS/TPD of their intended Level of training in writing by 31 August 2023
* All trainees entering ST6 in August 2024 must inform HoS/TPD in writing by 31 August 2023 if they are intending to remain on the old curriculum from August 2024
 |
| 31 December 2023  | * Finalise Roadmap for all trainees in terms of Level of entry to Curriculum 2024
* Identify any potential competition to Level 4 SIA posts
 |
| 1 February 2024  | * Deadline for applications to Level 4
* Rotations for Curriculum 2024 planned
 |
| 1 March 2024  | * Decision on Level 4 SIA post allocation
 |
| 1 April 2024  | * Allocation of rotations for August 2024
 |
| 15 June 2024  | * All ARCP reviews for 2024 to be completed
* One week deadline for all Outcome 5
 |
| 30 June 2024  | * ARCP forms on old ePortfolio will NOT be available
 |
| 1 July 2024  | * Trainees will no longer be able to use the old ePortfolio
 |
| July 2024  | * Switch to new ePortfolio
 |